## summary
McKnight Crossings Church - Auditorium Lighting Project
Elite Enterprises Proposal & Payment Reconcilliation
|  |  |  | (A) | [6 empty] | (B) |  | (A) - (B)
. | … |  | . | Proposal | . | INV10564 | INV10699 | INV10711 | INV10735 | . | TOT INVs | . | Δ | .
House Lighting:
| M | Crestron CP4 4-series Control System |  | 1695 |  | 1695 |  |  |  |  | 1695 |  | 0
| M | Crestron 7" Touch Screen |  | 395 |  | 395 |  |  |  |  | 395 |  | 0
| M | Crestron CEN-IO-RY-104 ethernet module w/4 relays |  | 945 |  | 945 |  |  |  |  | 945 |  | 0
| M | Crestron C2N-CBD-PBS Keypad |  | 295 |  | 295 |  |  |  |  | 295 |  | 0
| M | Custom Lightng Control Relay panel, 12 relays |  | 455 |  | 455 |  |  |  |  | 455 |  | 0
| M | Custom Lightng Control Relay panel, 8 relays |  | 355 |  | 355 |  |  |  |  | 355 |  | 0
| M | Misc Bulk cable, connectors, etc. |  | 250 |  | 250 |  |  |  |  | 250 |  | 0
| L | Installation (estimate) |  | 1520 |  |  | 2280 |  |  |  | 2280 |  | -760
| L | Programming |  | 2450 |  |  | 2450 |  |  |  | 2450 |  | 0
| L | Electrical Work |  | 1495 | [6 empty] | 0 |  | 1495
| M | Total Materials | 4390
| L | Total Labor | 5465
|  | TOTAL HOUSE LIGHTING |  | 9855 |  | 4390 | 4730 | 0 | 0 |  | 9120 |  | 735
Stage Lighting:
| M | 5 Mega Systems 7060-WW2 250W White LED |  | 7495 |  | 7495 |  |  |  |  | 7495 |  | 0
| M | 2 Mega Systems 7060-Q2W 250W RGBWW LED |  | 2998 |  | 2998 |  |  |  |  | 2998 |  | 0
| M | 4 Mega Systems 7060-LENS-36 |  | 916 |  | 916 |  |  |  |  | 916 |  | 0
| M | 2 Mega Systems 7060-LENS-26 |  | 458 |  | 458 |  |  |  |  | 458 |  | 0
| M | 1 Mega Systems 7060-LENS-19 |  | 229 |  | 229 |  |  |  |  | 229 |  | 0
| M | 1 Entec 71020 DIN-ODE Ethernet Gateway |  | 295 |  | 295 |  |  |  |  | 295 |  | 0
| M | Misc Bulk cable, connectors, etc. |  | 400 |  | 400 |  |  |  |  | 400 |  | 0
| L | Installation (estimate) |  | 1900 |  |  | 1900 |  | 1515 |  | 3415 |  | -1515
| L | Programming |  | 3150 |  |  | 3150 |  |  |  | 3150 |  | 0
| L | Electrical Work |  | 2495 | [8 empty] | 2495
| M | Total Materials | 12791
| L | Total Labor | 7545
|  | TOTAL STAGE LIGHTING |  | 20336 |  | 12791 | 5050 | 0 | 1515 |  | 19356 |  | 980
|  | PROJECT TOTAL |  | 30191 |  | 17181 | 9780 | 0 | 1515 |  | 28476 |  | 1715
CHANGE ORDER [12276]
Stage Lighting:
|  | supply and install 2 20amp, 120v circuits |  | 3800 |  |  |  | 3175 |  |  | 3175 |  | 625
|  | customer to supply lift | [5 empty] | 423.75 |  |  | 423.75 |  | -423.75
|  | TOTAL CHG ORDER |  | 3800 |  |  |  | 3598.75 |  |  | 3598.75 |  | 201.25
|  | PROJECT TOTAL |  | 33991 | [6 empty] | 32074.75 |  | 1916.25

## Proposal
. | . | . | .

## CHG12276
.

## INV10564
.

## INV10699
.
Attached is the labor invoice for your lighting project.

## INV10711
.
Attached is the invoice for the Third-Party Electrical Contractor plus management fee per Change Order #12276 and the pass thru charge for the lift rental.

## INV10735
. | .